## Project Planner
ADVANCED PHYSICAL COMPUTING
[5 empty] | CURRENT WEEK: | 1 |  |  | PLAN DURATION | [5 empty] | ACTUAL START |  |  |  |  | % COMPLETE | ACTUAL (BEYOND PLAN) | % COMPLETE (BEYOND PLAN) | DEADLINE
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | WEEKS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Design
Base model completed | 1 | 2 | 1 |  | 50%
Base model printed | 2 | 1 |  |  | 0%
Implementation
Components individually implemented | 1 | 2 | 1 |  | 20%
Components implemented in full circuit | 3 | 4 |  |  | 0%
Components installed into base model | 7 | 1
Testing
User testing | 8 | 2 |  |  | 0%
Report
Introduction | 1 | 3 | 1 |  | 50%
Background | 1 | 3 | 1 |  | 50%
Specification | 3 | 3 |  |  | 0%
Design | 4 | 3 |  |  | 0%
Implementation and testing | 8 | 2 |  |  | 0%
Evaluation | 10 | 1 |  |  | 0%
Description of final product | 9 | 1 |  |  | 0%
Appraisal | 11 | 1 |  |  | 0%
Summary and conclusions | 12 | 1 |  |  | 0%
Recommendations for future work | 12 | 1 |  |  | 0%
Other
Create user/technical manual | 10 | 2 |  |  | 0%
Deadlines
Degree show website content submission
Final report + appendices submission
Presentation/Demo

## Dates
WEEKS
1 | Jan 25th 2021
2 | Feb 1st 2021
3 | Feb 8th 2021
4 | Feb 15th 2021
5 | Feb 22nd 2021
6 | Mar 1st 2021
7 | Mar 8th 2021
8 | Mar 15th 2021
9 | Mar 22nd 2021
10 | Mar 29th 2021
11 | Apr 5th 2021
12 | Apr 12th 2021
13 | Apr 19th 2021
14 | Apr 26th 2021